## Projects
Title | Type | Priority | Kanban | Status | Tags | Owner | DueDate | StartDate | NextAction | BlockedBy | Links | Notes | CreatedOn | UpdatedOn
Enable full access + stable integrations: Trello + Drive (skills/MCP) | Ops | High | Doing | In progress | High, Ops | [5 empty] | https://trello.com/c/uizfCuGh/22-enable-full-access-stable-integrations-trello-drive-skills-mcp | HIGH PRIORITY. Goal: Morty must be able to READ/WRITE Trello boards/cards and READ/WRITE Drive (and ideally create Google Docs) via proper skills/MCP auth. Checklist: - Install/enable Trello skill + authenticate (read/write) - Install/enable Google Workspace/Drive tooling (MCP or skill) with read/write - Confirm Morty can: list cards, update cards, create docs/files, read sheets - Document where creds live + permission model (least-privilege if possible) | 2026-02-04T20:57:36.557Z | 2026-02-04T20:57:36.557Z
Build a Kanban board for the TODO list (visual tracking) | Frontend | High | Done | Done | High, Hobbies | [5 empty] | https://trello.com/c/t4PbSrPN/12-build-a-kanban-board-for-the-todo-list-visual-tracking | Section: Hobbies Priority: High Progress: Not started Notes: Could be Trello/Notion/Linear/GitHub Projects or a simple self-hosted board. | 2026-02-01T14:22:54.948Z | 2026-02-01T14:22:54.948Z
Enable n8n API key / programmatic management (so Morty can build workflows) | Automation | Medium | Done | Done | Hobbies, Medium | [5 empty] | https://trello.com/c/713RtiHF/17-enable-n8n-api-key-programmatic-management-so-morty-can-build-workflows | Later task: enable n8n API access (PAT/API key) and store it securely on the VPS. This lets Morty create/update workflows without manual clicking. | 2026-02-03T22:24:45.316Z | 2026-02-03T22:24:45.316Z
Set up n8n/Zapier (evaluate if needed on VPS) | Automation | Low | Done | Done | Hobbies, Low | [5 empty] | https://trello.com/c/QPWeU56K/5-set-up-n8n-zapier-evaluate-if-needed-on-vps | Section: Hobbies Priority: Low Progress: Not started | 2026-02-03T22:24:31.928Z | 2026-02-03T22:24:31.928Z
Put n8n behind HTTPS + domain (Caddy/NGINX reverse proxy + TLS) | Automation | Medium | Done | Done | Hobbies, Medium | [5 empty] | https://trello.com/c/eJl9IouD/15-put-n8n-behind-https-domain-caddy-nginx-reverse-proxy-tls | Add a domain (e.g. n8n.<domain>) pointing to the VPS, then reverse proxy :5678 behind HTTPS. Re-enable secure cookies afterwards. | 2026-02-03T15:39:51.569Z | 2026-02-03T15:39:51.569Z
Finish Google API connections | Project | Medium | Done | Done | Hobbies, Medium | [5 empty] | https://trello.com/c/uFpJKpS1/4-finish-google-api-connections | Section: Hobbies Priority: Medium Progress: In progress | 2026-02-03T20:54:46.492Z | 2026-02-03T20:54:46.492Z
OpenClaw | Project | Medium | Done | Done | [6 empty] | https://trello.com/c/8OvyUY4B/16-openclaw | Test | 2026-02-02T09:27:49.348Z | 2026-02-02T09:27:49.348Z
Design + host a new website for the company | Frontend | Low | Backlog | Not started | Hobbies, Low | [5 empty] | https://trello.com/c/hZ5Rlt2H/6-design-host-a-new-website-for-the-company | Section: Hobbies Priority: Low Progress: Not started | 2026-02-01T14:20:26.569Z | 2026-02-01T14:20:26.569Z
Design + host a website for your consulting automation services | Frontend | Low | Backlog | Not started | Hobbies, Low | [5 empty] | https://trello.com/c/AKUa96gf/7-design-host-a-website-for-your-consulting-automation-services | Section: Hobbies Priority: Low Progress: Not started | 2026-02-01T14:20:26.992Z | 2026-02-01T14:20:26.992Z
Assets monitoring tool (stocks/crypto/real estate) + newsletter of opportunities | Project | Low | Backlog | Not started | Hobbies, Low | [5 empty] | https://trello.com/c/hxAP8lWa/8-assets-monitoring-tool-stocks-crypto-real-estate-newsletter-of-opportunities | Section: Hobbies Priority: Low Progress: Not started | 2026-02-01T14:20:27.467Z | 2026-02-01T14:20:27.467Z
Fortune-cookie-style micro-gift subscription (fortune notes/cookies) — explore concept | Project | Low | Backlog | Not started | Hobbies, Low | [5 empty] | https://trello.com/c/gRw4A3vw/9-fortune-cookie-style-micro-gift-subscription-fortune-notes-cookies-explore-concept | Section: Hobbies Priority: Low Progress: Not started Notes: Fun idea; sanity-check shipping/unit economics + positioning. | 2026-02-01T14:20:27.937Z | 2026-02-01T14:20:27.937Z
OpenAI API key embeddings for memory_search (restore semantic memory) | Project | Low | Backlog | Not started | Hobbies, Low | [5 empty] | https://trello.com/c/E95I0tVb/10-openai-api-key-embeddings-for-memorysearch-restore-semantic-memory | Section: Hobbies Priority: Low Progress: Not started Notes: Current memory_search failed due to embeddings quota; switch to API key-based embeddings. | 2026-02-01T14:20:28.358Z | 2026-02-01T14:20:28.358Z
Custom restaurant chatbot for fast food business | Project | Low | Backlog | Not started | Hobbies, Low | [5 empty] | https://trello.com/c/8C8Sf8E2/11-custom-restaurant-chatbot-for-fast-food-business | Section: Hobbies Priority: Low Progress: Not started Notes: Define channels (web/WhatsApp), menu ingestion, ordering flow, handoff. | 2026-02-01T14:20:28.802Z | 2026-02-01T14:20:28.802Z
Daily/weekly email summary of our chats (cron → email) | Project | Low | Backlog | Not started | Hobbies, Low | [5 empty] | https://trello.com/c/CclNMbZw/13-daily-weekly-email-summary-of-our-chats-cron-%E2%86%92-email | Section: Hobbies Priority: Low Progress: Not started Notes: Possible via Gmail MCP draft/send with confirmation; schedule later after configuration is stable. | 2026-02-01T14:20:29.641Z | 2026-02-01T14:20:29.641Z
Rotate Trello API token (revoke old token + store new token securely) | Project | Medium | Backlog | Not started | Hobbies, Medium | [5 empty] | https://trello.com/c/PYItaia1/14-rotate-trello-api-token-revoke-old-token-store-new-token-securely | Security maintenance: rotate/revoke Trello token we pasted during setup. Update n8n credentials + any scripts. | 2026-02-01T14:27:49.101Z | 2026-02-01T14:27:49.101Z
Build Phase 1 Costs Sheet automation: n8n webhook → Google Sheets upsert + weekly digest | Automation | High | Backlog | Not started | High, Hobbies | [5 empty] | https://trello.com/c/ovSaSMeE/18-build-phase-1-costs-sheet-automation-n8n-webhook-%E2%86%92-google-sheets-upsert-weekly-digest | Create n8n workflows: costs_upsert (POST /costs/upsert) and costs_digest (weekly Telegram). Uses Morty Google Sheets credential and sheet ID 11Z6E6F_UZRK5n7dkeQHAsmiexZJDW0QUVAjp3YtWqbc, tab "Cloud Stack Costs - Services". | 2026-02-03T17:19:03.152Z | 2026-02-03T17:19:03.152Z
New item | Project | Medium | Backlog | Not started | [6 empty] | https://trello.com/c/WGJ0PjlG/19-new-item |  | 2026-02-03T21:52:21.438Z | 2026-02-03T21:52:21.438Z
Webhook-created Trello card | Automation | Medium | Backlog | Not started | [6 empty] | https://trello.com/c/QMNEXYCx/20-webhook-created-trello-card | Now reading from $json.body | 2026-02-03T21:54:24.904Z | 2026-02-03T21:54:24.904Z
Airbnb deal finder automation (cheapest listings by location + season) | Project | Low | Backlog | Not started | Hobbies, Low | [5 empty] | https://trello.com/c/4CXKgomF/21-airbnb-deal-finder-automation-cheapest-listings-by-location-season | Brainstorm: automation to fetch cheapest Airbnbs for a given location/date range and send digests. Investigate viability of Airbnb MCP servers vs browser automation vs paid data providers. | 2026-02-03T22:34:12.517Z | 2026-02-03T22:34:12.517Z
Resources Repo (Google Sheet): review + weekly discovery digest + assisted updates (future n8n) | Automation | Medium | Backlog | Not started | Automation, Medium | [5 empty] | https://trello.com/c/0DaUCcZd/23-resources-repo-google-sheet-review-weekly-discovery-digest-assisted-updates-future-n8n | Goal - Review/enhance the new Google Sheet "Resources Repo" (structure, columns, consistency). - Set up a weekly Telegram digest of newly found resources (skills/MCPs/agentic automation/AI startups/etc). - Human-in-the-loop: Atlas approves which links to keep. - Then append approved items to the sheet automatically (planned via n8n once Drive/Sheets access is fully configured). What we need from Atlas - Google Sheet link or file id - Which tab(s) are canonical - Any must-have columns (tags, type, source, summary, date added, confidence) Deliverables - A Drive Markdown spec describing the schema + workflow - (Later) n8n workflow: discovery → digest → approval → append to sheet Notes - Sources: Reddit, GitHub, X, web search, newsletters. - Keep dedupe + quality filters (avoid spam, dead links). | 2026-02-04T22:14:02.104Z | 2026-02-04T22:14:02.104Z
Buy mac mini and install second instance of open claw with new knowledge and docs | Project | Medium | Backlog | Not started | [6 empty] | https://trello.com/c/W8O7LPdZ/24-buy-mac-mini-and-install-second-instance-of-open-claw-with-new-knowledge-and-docs |  | 2026-02-05T13:20:49.244Z | 2026-02-05T13:20:49.244Z
Enable a second brain/model for Morty | Ops | High | Backlog | Not started | High, Ops | [6 empty] | Use Kimi or Gemini | 2026-02-06
Automations/backend skills user guide | Automation | High | Doing | In progress | Automation, Medium | [6 empty] | Use repositories and browsing/scraping | 2026-02-06
Wetaca Automation | Automation | Medium | Backlog | Not started | Automation, Medium | [7 empty] | 2026-02-06

## Personal Stuff
Title | Type | Priority | Kanban | Status | Tags | Owner | DueDate | NextAction | BlockedBy | Links | Notes | CreatedOn | UpdatedOn
Test company CRM for Monday demo | Project | High | Done | Done | High, Personal | [5 empty] | https://trello.com/c/AaeBV0p8/2-test-company-crm-for-monday-demo | Section: Personal Priority: High Progress: In progress | 2026-02-03T21:00:06.540Z
Renovate passport and visas | Project | High | Backlog | Not started | High, Personal | [5 empty] | https://trello.com/c/HgvNm4Wj/1-renovate-passport-and-visas | Section: Personal Priority: High Progress: Not started | 2026-02-01T14:20:24.384Z
Migrate one Playwright project to the VPS server | Project | Medium | Backlog | Not started | Medium, Personal | [5 empty] | https://trello.com/c/xrcmmftG/3-migrate-one-playwright-project-to-the-vps-server | Section: Personal Priority: Medium Progress: Not started | 2026-02-01T14:20:25.257Z